## Sheet1
Kelompok | NYUU |  |  | www.goodoldmanoj.com
TI-A PG |  |  |  | Belajar dasar bahasa jepang
Burn down chart
| Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
| Belajar dasar bahasa jepang | Hiragana | gojoun | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | dakuon | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | han-dakuon | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
|  |  | yoon | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0
|  | Katakana | gojoun | 8 | 8 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0
|  |  | dakuon | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | han-dakuon | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  |  | yoon | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0
|  | example |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  | 60 | 59 | 58 | 56 | 54 | 49 | 42 | 36 | 29 | 20 | 15 | 10 | 0
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on H5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered