## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Belajar dasar bahasa jepang | Hiragana | gojoun | 3 | 4 | 0 | 0 | 0 | 0
|  | dakuon | 1 | 2 | 3 | 5 | 2 | 0
|  | han-dakuon | 1 | 5 | 3 | 2 | 2 | 0
|  | yoon | 3 | 8 | 8 | 8 | 7 | 0
| Katakana | gojoun | 3 | 8 | 8 | 8 | 8 | 0
|  | dakuon | 1 | 9 | 9 | 9 | 9 | 0
|  | han-dakuon | 1 | 5 | 5 | 5 | 5 | 0
|  | yoon | 3 | 3 | 3 | 3 | 3 | 7
| example |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Ideal - Remaining efforts in uninterrupted working hours |  |  | 36 | 33 | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 36 | 64 | 59 | 60 | 56 | 27 | 0 | 20 | 20 | 20 | 20 | 20 | 20
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on H5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered